## Scrims
ID | Name | Phase | Kind | Status | Weight % | Earned % | XP | Commit | Notes
F1 | Repo bootstrap + monorepo structure | Foundations | Foundation | Completed | 4 | 4 | 20 | 0e4954c | Docs + workspace layout
F2 | Backend Express + TS foundation | Foundations | Foundation | Completed | 5 | 5 | 25 | 2940927 | Express 5 + tsx watch
F3 | Frontend Vite + React + TS + Tailwind | Foundations | Foundation | Completed | 5 | 5 | 25 | 4510707 | Tailwind, Vite config
F4 | Integration contracts baseline (docs) | Foundations | Foundation | Completed | 4 | 4 | 20 | fa93827 | ARCHITECTURE.md, contracts.md
F5 | Typed env validation (Zod) | Foundations | Foundation | Completed | 5 | 5 | 25 | 533b6b7 | Fail-loud at startup
L1 | IntegrationError contract module | Workday | Level | Completed | 3 | 3 | 25 | 8ec3e06 | Stable error codes + correlationId
L2 | Workday Bridge - axios adapter + interceptors | Workday | Level | Completed | 4 | 4 | 64 | bec48c6 | Bonus: request logger
L2.5 | Workday smoke route + getWorkday helper | Workday | Level | Completed | 3 | 3 | 30 |  | Thin client helper pattern
L3 | Phantom Workday - mock layer + WORKDAY_MODE | Workday | Level | Completed | 2 | 2 | 20 | d4527dc | Env flag committed; mock layer follow-up
L4 | Workday -> ValidatedUser mapping | Workday | Level | Pending | 3 | 0 | 0 |  | Blocked on real Workday creds
M4.1 | EAM Bridge - axios adapter (mirror of Workday) | EAM | Mini-quest | Completed | 4 | 4 | 51 |  | Bonus: duration logging
M4.2 | EAM helpers (getEam + postEam) | EAM | Mini-quest | Completed | 2 | 2 | 23 |  | Two-generic POST pattern
M4.4 | Real auth wiring (Basic + tenant/role/org) | EAM | Mini-quest | Completed | 3 | 3 | 30 | a2ff977 | Bonus: masked startup log
M4.5 | First Real Call - assets smoke route | EAM | Mini-quest | Completed | 3 | 3 | 39 | ed1c3f6 | Live Vopak data verified
M4.6 | Unwrap the envelope (Result.ResultData) | EAM | Mini-quest | In Progress | 2 | 1 | 0 |  | Anti-corruption layer pattern
M4.7 | Map to canonical EquipmentOption DTO | EAM | Mini-quest | Pending | 3 | 0 | 0 |  | First real DTO mapping
M5.1 | Sites/Departments mapping (terminal lookup) | EAM | Mini-quest | Pending | 3 | 0 | 0 |  | OrganizationContext DTO
M5.2 | Problem codes mapping | EAM | Mini-quest | Pending | 2 | 0 | 0 |  | ProblemCodeOption DTO
M5.3 | Work-order POST + create flow | EAM | Mini-quest | Pending | 5 | 0 | 0 |  | First real POST integration
L5 | Backend business route handlers (5 endpoints) | Business Logic | Level | Pending | 6 | 0 | 0 |  | Replaces /smoke routes
L6 | Workflow orchestration service (agent core) | Business Logic | Level | Pending | 8 | 0 | 0 |  | Coordinates Workday + EAM steps
L7 | Frontend state mgmt + workflow UI | Frontend | Level | Pending | 11 | 0 | 0 |  | Wire each workflow step
L8 | AI guidance layer (OpenAI integration) | AI | Level | Pending | 5 | 0 | 0 |  | Guidance only, not source of truth
L9 | Tests + e2e validation | Tests | Level | Pending | 2 | 0 | 0 |  | Smoke + integration
L10 | Deployment + docs polish | Deploy | Level | Pending | 2 | 0 | 0 |  | Hosting, README, runbook
TOTAL |  |  |  |  | 99 | 48 | 397

## Phase Summary
Phase | Total Weight % | Earned % | Status | # Items | # Done
Foundations | 23 | 23 | Done | 5 | 5
Workday | 15 | 12 | In Progress | 5 | 4
EAM | 27 | 13 | In Progress | 9 | 4
Business Logic | 14 | 0 | Not Started | 2 | 0
Frontend | 11 | 0 | Not Started | 1 | 0
AI | 5 | 0 | Not Started | 1 | 0
Tests | 2 | 0 | Not Started | 1 | 0
Deploy | 2 | 0 | Not Started | 1 | 0
PROJECT TOTAL | 99 | 48 | 48.5% | 25 | 13